## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Development Gantt Chart |  |  |  |  | COMPANY NAME | [6 empty] | Smarta | [14 empty] | Developer 1
PROJECT MANAGER |  | David Fox |  |  |  |  | DATE | [6 empty] | 2020-08-04 | [14 empty] | Developer 2
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE - TESTING/BUFFER TIME
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Tenant Features
1.1 | Property Hunting | Dev 1 | 2020-10-05 | 2020-10-23 | 15 | 0% | bar: WEEK 4 M to WEEK 6 F
1.2 | One-Click Application | Dev 1 | 2020-10-26 | 2020-11-13 | 15 | 0% | bar: WEEK 7 M to WEEK 9 F
1.3 | Roomamate Finder | Dev 1 | 2020-11-16 | 2020-12-04 | 15 | 0% | bar: WEEK 10 M to WEEK 12 F
1.4 | Dashboard | Dev 2 | 2020-10-26 | 2020-11-13 | 15 | 0% | bar: WEEK 7 M to WEEK 9 F
2 | Landlord Features
2.1 | Property Listing | Dev 1 | 2020-09-14 | 2020-10-02 | 15 | 0% | bar: WEEK 1 M to WEEK 3 F
2.2 | One-Click Application | Dev 1 | 2020-10-26 | 2020-11-13 | 15 | 0% | bar: WEEK 7 M to WEEK 9 F
2.3 | Dashboard | Dev 2 | 2020-11-16 | 2020-12-04 | 15 | 0% | bar: WEEK 10 M to WEEK 12 F
3 | Common Features
3.1 | Chat | Dev 2 | 2020-09-28 | 2020-10-23 | 20 | 0% | bar: WEEK 2 M to WEEK 6 F
3.2 | User Profiles | Dev 2 | 2020-09-14 | 2020-10-02 | 15 | 0% | bar: WEEK 1 M to WEEK 3 F
4 | Testing/Buffer Time
4.1 |  |  |  |  | 0 | 0%
4.2 |  |  |  |  | 0 | 0%
4.3 |  |  |  |  | 0 | 0%
4.4 |  |  |  |  | 0 | 0%

## Task List
Quick Stats |  |  |  | Dev 1 Task
Number of Weeks | 12 | 15 including testing |  | Dev 2 Task
Number of Epics | 8 | 4 each developer | 4 epics in 12 weeks for each developer
Tenants |  |  | Property Manager |  | Common
Roommate Finder Milestones |  |  | Property Listing Milestones |  | Chat Milestones
Task List |  |  | Task List |  | Task List
Create Student Profile |  |  | Upload property pictures |  | Chat between tenants
Personality Quiz (optional) |  |  | Select property locations |  | Chat between tenants and landlords
Roommate Preferences |  |  | Add property details |  | Pin important messages
Filtering Mechanism |  |  | Apply application template |  | Send images
Tinder View or List View |  |  |  |  | Add to personal shortlist
Request Connection |  |  | Dashboard Milestones |  | Chat storage to local
Roommate shortlists |  |  | Task List
Check/edit properties
Property Hunting Milestones |  |  | Check residents |  | User Profiles Milestones
Task List |  |  | Check payments/outstanding fees |  | Task List
Map View of All Properties |  |  | Active Applications |  | Upload/change profile pic
Filters |  |  | Issues/Requests |  | List roommates
Property information |  |  |  |  | Edit/add bio
Property Badges |  |  | One-Click Application Milestones |  | Add pictures
Property Shortlists |  |  | Task List
Application queues
One-Click Application Milestones
Task List
Application Preprocessing
Application prompting (more info)
Apply alone/ with roommates button
Dashboard Milestones
Task List
View/Make payments using API
View roommates
View rent/utilities
Shortlists
Issues/Requests

## API sheet
Chat Milestones
1) Flutter and Stream, Stream API Pricing
2) Free - Dash Chat
3) FireBase + MessageKit API, MessageKit Github
Property Hunting Milestones
Google Maps API Pricing
Roommate Finder Milestones
Find Roommate UI
Pub Dev API - Open Source
Filtering API
Dashboard Milestones
Google Pay API
Apple Pay API