## Epics remaining
Epics | Epic Size | Done | Completion % | Notes | Action
Develop General Screens and Processes | 25 | 0 | 0
Login | 5
Sign Up | 7
My Home | 1
Student Profile | 3
Property Manager Profile | 2
Property Listing | 2
Roommates Page | 3
Integrate Application Routing | 1
Firebase Connectivity | 1
Integrate Smarta Choice Features | 9 | 0 | 0
Instant Messaging | 5
Rent Payments | 2
Maintenance Reporting | 2
Develop Property Manager Side of App | 16 | 0 | 0
Adding a listing to process | 2
Adding a student to property | 2
Oversight screen of all properties and units | 3
Messaging | 5
Maintenance reports | 2
Rent collection | 2
Develop student side of App | 9 | 0 | 0
Rent Payment | 2
Maintenance report | 2
Messaging | 5
Develop property searching process of app | 15 | 0 | 0
Listing Overview | 2
Smarta Search Algorithm | 2
Roommate Searching | 3
Application review and Sign | 3
Lease Agreement Review and Sign | 1
Tour Booking | 2
Student Signing Algorithm | 2
Front Facing Sales Site | 15 | 0 | 0
Home Page | 2
Smarta Students Page | 2
Smarta Managers Page | 2
Universities and Colleges Page | 2
Blog Page | 2
Final Edits | 3
Integrate SWA needs | 2
TALLY
Total Epics | 89
Total Epics Done | 0
Percentage Completed | 0

## Epic Burndown
Sprint review dates | Expected epic points remaining | Actual Epic points remaining | Epic points done | Velocity
Sprint 1 - October 2nd | 80
Sprint 2 - October 9th | 75
Sprint 3 - October 16th | 70
Sprint 4 - October 23rd | 65
Sprint 5 - October 30th | 60
Sprint 6 - November 6th | 55
Sprint 7 - November 13th | 50
Sprint 8 - November 20th | 45
Sprint 9 - November 27th | 40
Sprint 10 - December 4th | 35
Sprint 11 - December 11th | 30
Sprint 12 - December 18th | 25
Sprint 13 - December 25th | 20
Sprint 14 - January 1st | 18
Sprint 15 - January 8th | 15
Sprint 16 - January 15th | 13
Sprint 17 - January 22nd | 10
Sprint 18 - January 29th | 5
Sprint 19 - February 5th | 3
Sprint 20 - February 12th | 0