## Revision History (hidden)
History
Version | Date | Modified By |  | Changes
1 | 2019-01-14 | Nick Barba |  | Build out of initial risks.
Document Review and Sign-off
Name |  | Role |  | Action | Date Reviewed
Document References
Reference | Document |  | Link/Path

## Dashboard
Risk Dashboard
Protected Area : do not delete
[25 empty] | Probability | 5 | 0.05625 | 0.1125 | 0.225 | 0.45 | 0.9
|  |  | Total Current Risks: 3 | [6 empty] | Closed/Complete Risks: 0 | [6 empty] | OverDue Risks: 1 | [8 empty] | 4 | 0.04375 | 0.0875 | 0.175 | 0.35 | 0.7
|  |  | as of 01/05/2021 | [6 empty] | as of 01/05/2021 | [6 empty] | as of 01/05/2021 | [8 empty] | 3 | 0.03125 | 0.0625 | 0.125 | 0.25 | 0.5
| Probability | 5 |  | 1 |  |  |  | Probability | 5 | [5 empty] | Probability | 5 |  | 1 |  |  |  | Legend |  |  |  | 2 | 0.01875 | 0.0375 | 0.075 | 0.15 | 0.3
|  | 4 | [6 empty] | 4 | [6 empty] | 4 | [9 empty] | 1 | 0.00625 | 0.0125 | 0.025 | 0.05 | 0.1
|  | 3 |  |  |  | 2 |  |  | 3 | [6 empty] | 3 | [5 empty] | High | - |  |  |  | 1 | 2 | 3 | 4 | 5
|  | 2 | [6 empty] | 2 | [6 empty] | 2 | [5 empty] | Moderate | 0.3 |  |  |  | Impact
|  | 1 | [6 empty] | 1 | [6 empty] | 1 | [5 empty] | Low | 0.05
|  |  | 1 | 2 | 3 | 4 | 5 |  |  | 1 | 2 | 3 | 4 | 5 |  |  | 1 | 2 | 3 | 4 | 5 | [6 empty] | Not Complete
|  |  | Impact | [6 empty] | Impact | [6 empty] | Impact | [10 empty] | Closed/Rejected
Complete/Approved
|  |  | Current Short-term Risks: 0 | [6 empty] | Current Mid-term Risks: 2 | [6 empty] | Current Long-term Risks: 0
|  |  | impact in next 15 days | [6 empty] | impact in 15 to 60 days | [6 empty] | impact beyond 60 days
| Probability | 5 | [5 empty] | Probability | 5 | [5 empty] | Probability | 5
|  | 4 | [6 empty] | 4 | [6 empty] | 4
|  | 3 | [6 empty] | 3 |  |  |  | 2 |  |  | 3
|  | 2 | [6 empty] | 2 | [6 empty] | 2
|  | 1 | [6 empty] | 1 | [6 empty] | 1
|  |  | 1 | 2 | 3 | 4 | 5 |  |  | 1 | 2 | 3 | 4 | 5 |  |  | 1 | 2 | 3 | 4 | 5
|  |  | Impact | [6 empty] | Impact | [6 empty] | Impact
| ID | Process State |  | Area | Risk Description | [7 empty] | Timing | Contingency Plan |  |  |  |  | Mitigation Plan |  |  | Status | Risk Value | Responsible
| 1 | Working |  | Time | The development team is fairly new at building a platform from scratch, causing a risk of delayed task completion; and delayed project completion | [7 empty] | MT | The team can choose to accept the delay and schedule a new release date or bring in a consultant to pick up team velocity. |  |  |  |  | The team will speak with mentors experienced in software development (Quentin Rosso, for one) to receive guidance on team and project management. |  |  | Not Complete | Schedule | Dave Fox
| 2 | Working |  | Time | The intern team and co-founding team are in 3 different timezones, presenting risk deciding meeting times everyone can make. | [7 empty] | Past | If no times for meetings can be found, teams will be broken down into smaller groups and meetings willbe planned accordingly. |  |  |  |  | Meetings with the entire team are shorter and longer meetings are with smaller groups. |  |  | Not Complete | Schedule | Dave Fox
| 3 | Working |  | Quality | Lack of clear communication breeds possibility of missing important bugs or gaps in the development process. | [7 empty] | MT | [8 empty] | Not Complete | Schedule | Dave Fox
4
5

## Risk Log
Risk Log
Risk ID | Process State | RBS Level 1 | RBS Level 2 | Identification Date | Risk Description | Area | From | To | Root Cause | Contingency Plan | Mitigation Plan | Symptom(s) | Risk Value | Timing | Probability | Impact | Risk | Rate | DO NOT DELETE | DO NOT DELETE2 | Responsible | Status | Project Code
1 | Working | 2._Management | 2.01 Project Management | 2020-09-23 | The development team is fairly new at building a platform from scratch, causing a risk of delayed task completion; and delayed project completion | Time | 2020-09-23 | 2021-02-01 | Hiring a team of quick-learning and passionate developers that only lack in experience building a platform of this scale from scratch. | The team can choose to accept the delay and schedule a new release date or bring in a consultant to pick up team velocity. | The team will speak with mentors experienced in software development (Quentin Rosso, for one) to receive guidance on team and project management. | Delayed task completion, delayed beta testing, delayed launch date, potential burnout of valued interns | Schedule | MT | 3 | 4 | 0.25 | ¦¦¦¦¦¦ | Not Complete/3/4 | MT/Not Complete/3/4 | Dave Fox | Not Complete | Addressed
2 | Working | 2._Management | 2.01 Project Management | 2020-09-25 | The intern team and co-founding team are in 3 different timezones, presenting risk deciding meeting times everyone can make. | Time | 2020-09-25 | 2020-11-20 | Hiring for remote positions resulted in accepting exceptional talent from all over. | If no times for meetings can be found, teams will be broken down into smaller groups and meetings willbe planned accordingly. | Meetings with the entire team are shorter and longer meetings are with smaller groups. | Inability to plan necessary meetings in a timely manner, frustration felt by everyone | Schedule | Past | 5 | 2 | 0.1125 | ¦¦ | Not Complete/5/2 | Past/Not Complete/5/2 | Dave Fox | Not Complete | Addressed
3 | Working | 2._Management | 2.04 Communication | 2020-10-07 | Lack of clear communication breeds possibility of missing important bugs or gaps in the development process. | Quality | 2020-10-07 | 2021-02-01 | Lacking comprehensive understanding of software development from the founders. |  |  |  | Schedule | MT | 3 | 4 | 0.25 | ¦¦¦¦¦¦ | Not Complete/3/4 | MT/Not Complete/3/4 | Dave Fox | Not Complete | Addressed
4 |  | 3._Commercial | [16 empty] | // | ///
5 | [18 empty] | // | ///
6 | [18 empty] | // | ///
7 | [18 empty] | // | ///
8 | [18 empty] | // | ///
9 | [18 empty] | // | ///
10 | [18 empty] | // | ///
11 | [18 empty] | // | ///
12 | [18 empty] | // | ///
13 | [18 empty] | // | ///
14 | [18 empty] | // | ///
15 | [18 empty] | // | ///
16 | [18 empty] | // | ///
17 | [18 empty] | // | ///
18 | [18 empty] | // | ///
19 | [18 empty] | // | ///
20 | [18 empty] | // | ///
21 | [18 empty] | // | ///
22 | [18 empty] | // | ///
23 | [18 empty] | // | ///
24 | [18 empty] | // | ///
25 | [18 empty] | // | ///
26 | [18 empty] | // | ///
27 | [18 empty] | // | ///
28 | [18 empty] | // | ///
29 | [18 empty] | // | ///
30 | [18 empty] | // | ///
31 | [18 empty] | // | ///
32 | [18 empty] | // | ///
33 | [18 empty] | // | ///
34 | [18 empty] | // | ///
35 | [18 empty] | // | ///
36 | [18 empty] | // | ///
37 | [18 empty] | // | ///
38 | [18 empty] | // | ///
39 | [18 empty] | // | ///
40 | [18 empty] | // | ///
41 | [18 empty] | // | ///
42 | [18 empty] | // | ///
43 | [18 empty] | // | ///
44 | [18 empty] | // | ///
45 | [18 empty] | // | ///
46 | [18 empty] | // | ///
47 | [18 empty] | // | ///
48 | [18 empty] | // | ///
49 | [18 empty] | // | ///
50 | [18 empty] | // | ///
51 | [18 empty] | // | ///
52 | [18 empty] | // | ///
53 | [18 empty] | // | ///
54 | [18 empty] | // | ///
55 | [18 empty] | // | ///
56 | [18 empty] | // | ///
57 | [18 empty] | // | ///
58 | [18 empty] | // | ///
59 | [18 empty] | // | ///
60 | [18 empty] | // | ///
61 | [18 empty] | // | ///
62 | [18 empty] | // | ///
63 | [18 empty] | // | ///
64 | [18 empty] | // | ///
65 | [18 empty] | // | ///
66 | [18 empty] | // | ///
67 | [18 empty] | // | ///
68 | [18 empty] | // | ///
69 | [18 empty] | // | ///
70 | [18 empty] | // | ///
71 | [18 empty] | // | ///
72 | [18 empty] | // | ///
73 | [18 empty] | // | ///
74 | [18 empty] | // | ///
75 | [18 empty] | // | ///
76 | [18 empty] | // | ///
77 | [18 empty] | // | ///
78 | [18 empty] | // | ///
79 | [18 empty] | // | ///
80 | [18 empty] | // | ///
81 | [18 empty] | // | ///
82 | [18 empty] | // | ///
83 | [18 empty] | // | ///
84 | [18 empty] | // | ///
85 | [18 empty] | // | ///
86 | [18 empty] | // | ///
87 | [18 empty] | // | ///
88 | [18 empty] | // | ///
89 | [18 empty] | // | ///
90 | [18 empty] | // | ///
91 | [18 empty] | // | ///
92 | [18 empty] | // | ///
93 | [18 empty] | // | ///
94 | [18 empty] | // | ///
95 | [18 empty] | // | ///
96 | [18 empty] | // | ///
97 | [18 empty] | // | ///
98 | [18 empty] | // | ///
99 | [18 empty] | // | ///
100 | [18 empty] | // | ///
101 | [18 empty] | // | ///
102 | [18 empty] | // | ///
103 | [18 empty] | // | ///
104 | [18 empty] | // | ///
105 | [18 empty] | // | ///
106 | [18 empty] | // | ///
107 | [18 empty] | // | ///
108 | [18 empty] | // | ///
109 | [18 empty] | // | ///
110 | [18 empty] | // | ///
111 | [18 empty] | // | ///
112 | [18 empty] | // | ///
113 | [18 empty] | // | ///
114 | [18 empty] | // | ///
115 | [18 empty] | // | ///
116 | [18 empty] | // | ///
117 | [18 empty] | // | ///
118 | [18 empty] | // | ///
119 | [18 empty] | // | ///
120 | [18 empty] | // | ///
121 | [18 empty] | // | ///
122 | [18 empty] | // | ///
123 | [18 empty] | // | ///
124 | [18 empty] | // | ///
125 | [18 empty] | // | ///
126 | [18 empty] | // | ///
127 | [18 empty] | // | ///
128 | [18 empty] | // | ///
129 | [18 empty] | // | ///
130 | [18 empty] | // | ///
131 | [18 empty] | // | ///
132 | [18 empty] | // | ///
133 | [18 empty] | // | ///
134 | [18 empty] | // | ///
135 | [18 empty] | // | ///
136 | [18 empty] | // | ///
137 | [18 empty] | // | ///
138 | [18 empty] | // | ///
139 | [18 empty] | // | ///
140 | [18 empty] | // | ///
141 | [18 empty] | // | ///
142 | [18 empty] | // | ///
143 | [18 empty] | // | ///
144 | [18 empty] | // | ///
145 | [18 empty] | // | ///
146 | [18 empty] | // | ///
147 | [18 empty] | // | ///
148 | [18 empty] | // | ///
149 | [18 empty] | // | ///
150 | [18 empty] | // | ///
Formulas:
Timing = IF(OR([From]="",[To]=""),"",IF([To]<TODAY(),"Past",IF([To]<=Settings!$D11,Settings!$B11,IF([To]<=Settings!$D12,Settings!$B12,Settings!$B13))))

## Rules
Generic Impact Scales
| 1 Very Low | 2 Low | 3 Medium | 4 High | 5 Very High
Cost | Insignificant cost increase | < 5% cost increase | 5-10% cost increase | 10-20% cost increase | >20% cost increase
Schedule | Insignificant schedule slippage | Overall project slippage <5% | Overall project slippage 5-10% | Overall project slippage 10-20% | Overall project slippage >20%
Functionality | Functionality decrease barely noticeable | Minor areas of functionality are affected | Major areas of functionality are affected | Functionality reduction unacceptable to the client | Project end product is effectively useless
Quality | Quality degradation barley noticeable | Only very demanding applications are affected | Quality reduction requires client approval | Quality reduction unacceptable to the client | Project end product is effectively unusable
Generic Likelihood Scales
Level | Probability of Occurrence |  | Intervention Difficulty
1 | You would be surprised if this happens. |  | Your normal management process should easily ensure an acceptable outcome.
2 | Less likely to happen than not. |  | Careful oversight of your normal management process will probably bring about an acceptable outcome.
3 | Just as likely to happen as not. |  | Additional time and effort will be required to move toward an acceptable outcome.
4 | More likely to happen as not |  | Your resources and authority are sufficient to permit only minor effects on the outcome.
5 | You would be surprised if this did not happen. |  | Your ability to affect the outcome is effectively zero.

## Settings
General Info |  |  |  | Status
Project Total Value |  |  |  | Not Complete
Total Project Percentile Risk Value |  |  |  | Complete/Approved
Project Contingency Value |  |  |  | Closed/Rejected
Project duration (in days) | 188 |  |  | Project Code
Last RiskID | 21 |  |  | Addressed
On Hold
Term Settings |  |  |  | Escalated
ST | 15 | 2021-01-20 |  | No Activity
MT | 60 | 2021-03-06
LT | - | -
Probability and Impact |  |  |  |  | Probability - Impact Matrix
Probability | Prob. Value | Impact | Impact Value | 5 | 0.05625 | 0.1125 | 0.225 | 0.45 | 0.9
5 | 0.9 | 5 | 1 | 4 | 0.04375 | 0.0875 | 0.175 | 0.35 | 0.7
4 | 0.7 | 4 | 0.5 | 3 | 0.03125 | 0.0625 | 0.125 | 0.25 | 0.5
3 | 0.5 | 3 | 0.25 | 2 | 0.01875 | 0.0375 | 0.075 | 0.15 | 0.3
2 | 0.3 | 2 | 0.125 | 1 | 0.00625 | 0.0125 | 0.025 | 0.05 | 0.1
1 | 0.1 | 1 | 0.0625 |  | 1 | 2 | 3 | 4 | 5
Risk Thresholds
Low | 0.05
Moderate | 0.3
High | -
Risk Breakdown Structure
0._No_Project_Risks | 1._Technical | 2._Management | 3._Commercial | 4._External
0. Not more specified | 1. Not more specified | 2. Not more specified | 3. Not more specified | 4. Not more specified
| 1.00 No Technical Risks | 2.00 No Management Risks | 3.00 No Commercial Risks | 4.00 No External Risks
| 1.01 Scope Definition | 2.01 Project Management | 3.01 Contractual T&C's | 4.01 Legislation
| 1.02 Requirements Definition | 2.02 Organization | 3.02 Financing | 4.02 Regulatory
| 1.03 Technical Processes | 2.03 Resourcing | 3.03 Liabilities & Warranties | 4.03 Exchange Rates
| 1.04 Technical Interfaces | 2.04 Communication | 3.04 Payment Terms | 4.04 Sites/Facilities
| 1.05 Technology | 2.05 Information | 3.05 Suspension & Termination | 4.05 Competition
| 1.06 Performance | 2.06 Health, Safety & Environment | 3.06 Internal Procurement | 4.06 Weather
| 1.07 Reliability | 2.07 Reputation | 3.07 Subcontracts | 4.07 Political
| 1.08 Safety & Security |  | 3.08 Applicable Law | 4.08 Country
| 1.09 Test & Acceptance |  | 3.09 Partnering | 4.09 Pressure Groups
4.10 Force Majeure